CONCEPT NOTE Ndarinzwe Health Empowering Safe Motherhood Through Digital Support

PROJECT SNAPSHOT

| Project Title: | Ndarinzwe Health – Empowering Safe Motherhood Through Digital Support |
| --- | --- |
| Project Type: | Digital Health Platform (Mobile App + USSD + CHW Portal) |
| Target Group: | Pregnant women, postpartum mothers, and Community Health Workers in Rwanda |
| Geographic Focus: | Rwanda – Pilot in selected urban and rural districts |
| Pilot Duration: | 12 months (Phase 1) |
| Contact: | Kigali, Rwanda |
| Date: | June 2026 |

1.  Background and Problem Statement

Despite significant progress in maternal and child health, Rwanda continues to face critical gaps in antenatal and postnatal care utilization. According to the Rwanda Demographic and Health Survey (RDHS), only approximately 47% of pregnant women complete the recommended four antenatal care (ANC) visits, and fewer than 1% meet the World Health Organization (WHO) recommendation of eight visits. Missed or delayed care significantly increases the risk of preventable maternal and neonatal complications.

Maternal and newborn health challenges remain closely linked to several interacting barriers:

- Delayed care-seeking due to limited awareness of danger signs

- Inadequate maternal nutrition knowledge, especially during and after pregnancy

- Limited postpartum follow-up — the period after delivery is particularly high-risk, yet many mothers receive no continuous support once discharged

- Missed or forgotten immunization schedules for newborns

- Community Health Workers (CHWs) relying on manual systems for tracking, making consistent follow-up on missed appointments difficult

A key structural barrier is the lack of accessible, timely, and culturally appropriate maternal health information at the household level. Many women — particularly in rural areas — have limited access to smartphones or internet connectivity, creating an information gap between formal health services and the home.

As a result, many women miss essential antenatal and postnatal visits, fail to recognize warning signs early, and are not adequately supported in making informed, timely decisions for their health and that of their children.

2.  Proposed Solution

Ndarinzwe Health is a digital maternal and postpartum companion designed to support women throughout pregnancy, after delivery, and during early motherhood. The platform provides continuous guidance, reminders, and support to improve care-seeking behaviour and maternal well-being.

The platform delivers:

- Weekly pregnancy and postpartum guidance covering nutrition, maternal and newborn danger signs, and child immunization schedules

- Automated reminders for ANC and postnatal care visits, and family planning education

- An integrated chatbot enabling users to ask health questions and access targeted information in real time

- Basic mental health support through awareness messages, stress management guidance, and referral information for mothers requiring additional care

- Full bilingual interface in Kinyarwanda and English, with voice-reading functionality for users with limited literacy

To ensure universal inclusion, Ndarinzwe is accessible through two channels:

- Mobile Application — for smartphone users with internet access

- Full interactive interface with chatbot, reminders, progress tracking, and visual content

- USSD Platform — for women without internet access using basic phones

- Delivers the same essential information in text format; voice guidance in Kinyarwanda and English ensures non-literate users are not excluded

Community Health Workers are integrated into the system through a dedicated CHW portal that enables them to monitor registered women in their villages, track ANC and postnatal visit attendance, confirm completed appointments, and follow up on missed visits. This strengthens accountability and ensures digital engagement translates into real health outcomes.

3.  Innovation and Differentiation

Ndarinzwe Health is innovative in three key ways:

- Dual-access design: Unlike existing solutions that target smartphone users only, Ndarinzwe ensures equitable access through both a mobile app and a USSD channel, reaching rural and low-income mothers with basic phones

- CHW integration for accountability: The CHW portal links community-level engagement to facility attendance data in real time, creating a feedback loop that reduces missed appointments and strengthens continuity of care

- Holistic, single-platform approach: Ndarinzwe addresses maternal health, newborn care, child immunization, family planning, and mental health within one platform — bridging the gap between household-level support and formal healthcare services

While existing tools largely focus on facility-based reporting or single-function reminders, Ndarinzwe directly and continuously engages women throughout the pregnancy-to-postpartum journey in a culturally appropriate, language-accessible format.

4.  Expected Impact

Ndarinzwe Health is expected to generate measurable improvements across individual, community, and national levels.

Key Outcome Targets — Pilot Phase

| Key Indicator | Baseline | Pilot Target |
| --- | --- | --- |
| Completion of ≥4 ANC visits | ~47% | ≥70% |
| Adherence to 8-visit WHO recommendation | <1% | 10–15% |
| Postnatal care visit within 6 weeks | Suboptimal | Improved |
| Child immunization schedule adherence | Variable | Improved |
| Missed appointments via CHW tracking | Manual/high miss rate | Reduced |

At the community level, CHW integration will reduce missed appointments and improve continuity of care. Socially, the platform will empower women with reliable, culturally appropriate health information for informed decisions on pregnancy, family planning, and mental well-being.

Economically, preventing complications reduces the cost burden on families and enables mothers to remain active in their households and communities. In the long term, Ndarinzwe contributes to Rwanda's national priorities under SDG 3 (Good Health and Well-Being) and Vision 2050 by supporting safer pregnancies, healthier children, and stronger communities.

5.  Implementation Approach

Ndarinzwe Health will be implemented through a structured three-phase approach:

| Phase | Timeline | Key Activities |
| --- | --- | --- |
| Phase 1 – MVP & Pilot | Months 1–6 | Platform development (app + USSD + CHW portal); usability testing; pilot launch in 2–3 districts; onboarding of CHWs and first cohort of users. |
| Phase 2 – Evaluation & Refinement | Months 7–9 | Data collection and outcome analysis; user feedback integration; platform refinement; stakeholder engagement for scale-up. |
| Phase 3 – Scale-Up | Months 10–12 | Partnership development (RBC, telecoms, NGOs); national expansion planning; sustainability strategy finalization. |

Key implementation principles include meaningful community engagement, co-design with CHWs and end users, evidence-based content development aligned with Rwanda's national maternal health guidelines, and ongoing monitoring and evaluation throughout all phases.

6.  Team Capacity

Ndarinzwe Health is led by medical students from the University of Rwanda with strong knowledge in maternal and child health, public health, and community engagement. The team is committed to developing an evidence-based, scalable solution that aligns with national health priorities and responds to real community needs.

7.  Partnerships and Sustainability

To ensure long-term impact and scalability, Ndarinzwe Health will actively seek partnerships across the following sectors:

- Government / Health Sector: Rwanda Biomedical Centre (RBC), Rwanda Health Communication Centre (RHCC), and district health offices for content validation, CHW coordination, and potential integration into national health systems

- Telecommunications: MTN Rwanda and Airtel Rwanda for USSD channel infrastructure, potential zero-rating of data for app users, and SMS delivery partnerships

- Civil Society and NGOs: Organizations working in maternal health, gender, and community development for co-implementation, user outreach, and CHW training support

- Academic Institutions: University of Rwanda (CMHS) and research institutions for evidence generation, monitoring support, and ongoing evaluation

Sustainability will be pursued through a mixed revenue model, including grant funding during the pilot phase, institutional partnerships for scale, and exploration of low-cost subscription or mobile money–based models for long-term platform maintenance.

8.  Budget Overview

| NDARINZWE HEALTH – DETAILED BUDGET BREAKDOWN |  |  |  |  |
| --- | --- | --- | --- | --- |
| Pilot Phase – 12 Months ¦ Total: 10,000,000 RWF ¦ June 2026 |  |  |  |  |
| Line Item Description | Amount (RWF) | % Cat. | Qty/Units | Unit Cost (RWF) |
| 1. TECHNOLOGY DEVELOPMENT |  |  |  |  |
| Mobile Application – UI/UX design and development | 900,000 RWF | 32.1% | 1 app | 900,000 |
| USSD platform development and integration | 600,000 RWF | 21.4% | 1 sys | 600,000 |
| CHW monitoring portal (web-based) | 500,000 RWF | 17.9% | 1 sys | 500,000 |
| AI chatbot development and integration | 350,000 RWF | 12.5% | 1 mod | 350,000 |
| Voice-reading feature (Kinyarwanda & English) | 200,000 RWF | 7.1% | 2 lang | 100,000 |
| Server hosting and cloud infrastructure (12 months) | 150,000 RWF | 5.4% | 12 mo | 12,500 |
| Platform testing, QA, and security audit | 100,000 RWF | 3.6% | 1 audit | 100,000 |
| SUBTOTAL – Technology Development | 2,800,000 RWF | 28.0% |  |  |
| 2. CONTENT DEVELOPMENT |  |  |  |  |
| Health content writing – pregnancy & postpartum | 200,000 RWF | 18.2% | 20 modules | 10,000 |
| Content review by maternal health expert / clinician | 150,000 RWF | 13.6% | 15 hours | 10,000 |
| Translation: English ↔ Kinyarwanda | 120,000 RWF | 10.9% | 12 docs | 10,000 |
| Voice recording – Kinyarwanda narrator | 130,000 RWF | 11.8% | 20 tracks | 6,500 |
| Voice recording – English narrator | 100,000 RWF | 9.1% | 20 tracks | 5,000 |
| Mental health content + referral directory | 100,000 RWF | 9.1% | 1 module | 100,000 |
| Immunization schedule integration (MOH aligned) | 80,000 RWF | 7.3% | 1 module | 80,000 |
| Family planning content development | 80,000 RWF | 7.3% | 1 module | 80,000 |
| Graphic/visual design for app content | 140,000 RWF | 12.7% | 14 screens | 10,000 |
| SUBTOTAL – Content Development | 1,100,000 RWF | 11.0% |  |  |
| 3. PILOT IMPLEMENTATION & CHW ENGAGEMENT |  |  |  |  |
| CHW training workshops (2 districts × 2 days) | 300,000 RWF | 16.7% | 4 days | 75,000 |
| CHW training materials and handbooks | 80,000 RWF | 4.4% | 40 kits | 2,000 |
| Community mobilization and user recruitment | 200,000 RWF | 11.1% | 2 dist. | 100,000 |
| User onboarding support and orientation sessions | 150,000 RWF | 8.3% | 10 sess. | 15,000 |
| Field coordinator (6 months, part-time) | 600,000 RWF | 33.3% | 6 months | 100,000 |
| District health office engagement and MoUs | 100,000 RWF | 5.6% | 2 dist. | 50,000 |
| Pilot monitoring visits (quarterly) | 200,000 RWF | 11.1% | 4 visits | 50,000 |
| SIM cards and USSD access support for rural users | 170,000 RWF | 9.4% | 170 users | 1,000 |
| SUBTOTAL – Pilot Implementation & Chw Engagement | 1,800,000 RWF | 18.0% |  |  |
| 4. MONITORING & EVALUATION |  |  |  |  |
| Baseline survey design and data collection | 150,000 RWF | 21.4% | 1 survey | 150,000 |
| Endline evaluation / impact assessment | 180,000 RWF | 25.7% | 1 eval | 180,000 |
| Data management platform / KoboToolbox setup | 70,000 RWF | 10.0% | 12 months | 5,833 |
| Mid-term review meeting | 80,000 RWF | 11.4% | 1 meeting | 80,000 |
| M&E officer / consultant (part-time, 3 months) | 150,000 RWF | 21.4% | 3 months | 50,000 |
| Final report writing and dissemination | 70,000 RWF | 10.0% | 1 report | 70,000 |
| SUBTOTAL – Monitoring & Evaluation | 700,000 RWF | 7.0% |  |  |
| 5. HUMAN RESOURCES |  |  |  |  |
| Project Lead / Medical Lead (12 months, part-time) | 800,000 RWF | 40.0% | 12 months | 66,667 |
| Digital Health Co-Lead (12 months, part-time) | 600,000 RWF | 30.0% | 12 months | 50,000 |
| Administrative / Finance Officer (part-time, 6 mo) | 300,000 RWF | 15.0% | 6 months | 50,000 |
| Research Assistant (data entry & support, 6 mo) | 300,000 RWF | 15.0% | 6 months | 50,000 |
| SUBTOTAL – Human Resources | 2,000,000 RWF | 20.0% |  |  |
| 6. PARTNERSHIPS & COMMUNICATIONS |  |  |  |  |
| Stakeholder engagement meetings and workshops | 100,000 RWF | 25.0% | 4 meetings | 25,000 |
| Presentation materials and pitch decks | 60,000 RWF | 15.0% | 3 events | 20,000 |
| Social media and digital outreach (12 months) | 80,000 RWF | 20.0% | 12 months | 6,667 |
| Press release and media outreach | 60,000 RWF | 15.0% | 1 launch | 60,000 |
| Partnership MoU legal review | 50,000 RWF | 12.5% | 2 MoUs | 25,000 |
| Translation of key documents for partners | 50,000 RWF | 12.5% | 5 docs | 10,000 |
| SUBTOTAL – Partnerships & Communications | 400,000 RWF | 4.0% |  |  |
| 7. OPERATIONS & ADMINISTRATION |  |  |  |  |
| Office consumables and printing (12 months) | 80,000 RWF | 11.4% | 12 months | 6,667 |
| Internet and communication costs (12 months) | 84,000 RWF | 12.0% | 12 months | 7,000 |
| Transport and field travel (team, 12 months) | 200,000 RWF | 28.6% | 12 months | 16,667 |
| Team meetings and internal workshops (quarterly) | 96,000 RWF | 13.7% | 4 meetings | 24,000 |
| Accounting and financial management | 120,000 RWF | 17.1% | 12 months | 10,000 |
| Miscellaneous operational costs | 120,000 RWF | 17.1% | 12 months | 10,000 |
| SUBTOTAL – Operations & Administration | 700,000 RWF | 7.0% |  |  |
| 8. CONTINGENCY RESERVE (5%) |  |  |  |  |
| Contingency – unforeseen technical costs | 200,000 RWF | 40.0% | Reserve | — |
| Contingency – field implementation overruns | 150,000 RWF | 30.0% | Reserve | — |
| Contingency – personnel / HR adjustments | 150,000 RWF | 30.0% | Reserve | — |
| SUBTOTAL – Contingency Reserve (5%) | 500,000 RWF | 5.0% |  |  |
| GRAND TOTAL | 10,000,000 RWF | 100.0% |  |  |